## Sheet1
Major ongoing and planned airport projects Updated: 18 February 2024 (see notes at bottom)
REGION | COUNTRY | AIRPORT | IATA CODE | PROJECT TYPE | GREENFIELD | PAX TRM | CGO TRM | MRO | ATC | AIRFIELD | LANDSIDE | PROJECT DETAILS | CAPEX (MLLN USD) | STATUS | STATUS DETAILS | ADDED/UPDATED
01 Europe | Albania | Flora | n/a | Greenfield | X | [6 empty] | New airport serving flora, Albania's 3rd most populous city: • 3,200 m runway • Passenger terminal • MRO and cargo facilities | 110 | Under construction | To become operational in 2025 | 2024-01-28
01 Europe | Austria | Salzburg | SZG | Redevelopment |  | X | [5 empty] | Rebuild of Terminal 1 | 80 | Planning | • As of August 2023 in design phase • Project to be executed between 2025 and 2031 | 2023-08-31
01 Europe | Austria | Vienna (1) | VIE | Expansion |  | X | [5 empty] | Expansion Terminal 3: • 70,000 m2, including waiting and lounge areas, bus gates, shopping, and restaurants. It will also facilitate convenient transfer connections between gates and centralize security checks | 460 | Under construction | Work to start in February 2024 and scheduled to be completed by 2027 | 2024-01-28
01 Europe | Austria | Vienna (2) | VIE | Expansion | [5 empty] | X |  | Third runway: • New 3,680 metre runway 11R/29L • 2,400 metres south parallel to the existing runway 11L/29R • Will be equipped with a CAT III ILS in runway direction 29L | 600-1,200 | Planning | • The first construction phase is now to be implemented by mid-2033 at the latest • Decision to be made in 2025 or 2026 | 2023-08-30
01 Europe | Belgium | Brussels (1) | BRU | Expansion | [6 empty] | X | Tramline connection between airport and Brussels North train station | TBD | Planning | Construction scheduled to start in 2025 | 2024-01-28
01 Europe | Belgium | Brussels (2) | BRU | Expansion |  | X |  |  |  |  | X | Major terminal expansion: • Extension Pier A • Construction of two new piers by 2035-2040 • Improved landside and airside infrastructure • Airport city development | Multi-billion-dollar Development | Planning | Long-term development
01 Europe | Belgium | Liege | LGG | Expansion |  |  | X | X |  | X |  | 2040 Master Plan: • Lengthening of emergency runway from 2,340 to 3,286 m • New taxiways, aircraft apron • New hangar for large aircraft • New cargo warehouses • Increase of annual movements to 55,000 • Freight volume to rise from 1.12 million tonnes in 2020 to 2.5 million tonnes in 2040 | 600 | Planning | To be executed by 2040
01 Europe | Bosnia and Herzegovina | Sarajevo | n/a | Greenfield | X | [6 empty] | New airport to be built at Visoko, thirty kilometres north of Sarajevo: • Would replace current airport, which is located on edge of city and is running out of space | TBD | Long-term development | • Idea has existed since WW2 • Relocation was last proposed during the general elections of 2022, by the Sarajevo branch of ruling political Party of Democratic Action (SDA)
01 Europe | Bosnia and Herzegovina | Sarajevo | SJJ | Expansion | [5 empty] | X |  | Rehabilitation and extension runway: • Extension from 2,600 metres to 3,150 metres in order to accommodate long-haul tourist flights | TBD | Planning
01 Europe | Bulgaria | Burgas | BOJ | Expansion | [6 empty] | X | Train connection to city | TBD | Feasibility |  | 2024-02-11
01 Europe | Bulgaria | Sofia (1) | SOF | Renovation |  | X |  |  |  | X |  | Refurbishment Terminal 2: • Installation of boarding bridges • Installation of a new baggage management system • Doubling capacity of check-in counters • Redevelopment of hand baggage and border control areas • New duty-free shopping area of almost 2,000 m2 Other works: • Rehabilitation airfield and runway | 83 (total) 23 (for T2 only) | Under construction | To be completed at the end of 2024, after which old T1 will close | 2023-05-13
01 Europe | Bulgaria | Sofia (2) | SOF | Expansion |  | X | [5 empty] | New terminal 3 | 750 | Planning | • In design stage • Construction scheduled to start at the end of 2026, or at the beginning of 2027 • To be completed by 2030 | 2023-05-13
01 Europe | Croatia | Pokrovnik | n/a | Greenfield | X | [6 empty] | New 'Heart of Dalmatia' airport serving Šibenik-Knin County on the Dalmation coast: • Cat 4C airport | TBD | Planning | In planning phase | 2023-08-30
01 Europe | Croatia | Pula | PUY | Expansion |  | X |  |  |  | X |  | Terminal and airfield expansion: • Runway extension with 250 m to 3,200 m • New terminal building | TBD | Feasibility | In feasibility stage
01 Europe | Czech Republic | Prague (1) | PRG | Expansion |  | X | [5 empty] | Terminal expansion: • New Pier D • Capacity to handle projected 21.2 mppa by 2028 | 1200 | Planning | To be constructed between 2026 and 2033 | 2023-08-31
01 Europe | Czech Republic | Prague (2) | PRG | Expansion |  | X |  |  |  | X | X | Medium to Long-term development: • Construction of parallel runway • Further expansion of T2 • Capacity raised to 24 mppa • Rail connection between airport and city • Airport City development | 1000 | Planning | Runway to be built between 2028 and 2031
01 Europe | Denmark | Copenhagen (1) | CPH | Renovation & Expansion |  | X | [5 empty] | Renovation and expansion Terminal 3: • New Baggage Handling System • 80,000 m2 expansion containing retail and F&B | 732 | Under construction | • Announced in May 2023 • Scheduled to be completed in 2029 | 2024-12-12
01 Europe | Denmark | Copenhagen (2) | CPH | Redevelopment & Expansion |  | X | [5 empty] | Terminal and expansion: • Rebuild and extension of existing boarding piers, • Construction of new boarding pier • Shortening of runway 12/30 by 600 metres to 2,200 metres as well as moving it 300 metres to the southwest • Gradual increase of capacity from 30 to 40 to mppa million, and potentially 55 mppa | TBD | Planning | In December 2023, the development plan was approved by Danish parliament | 2024-01-28
01 Europe | Estonia | Tallinn (2) | TLL | Expansion |  | X |  |  |  |  | X | Terminal expansion: • Increase of gates from 13 to 26 • Airport city development | TBD | Long-term development | Long-term development: Currently scheduled to be completed by 2035
01 Europe | Finland | Helsinki (1) | HEL | Expansion |  | X | [5 empty] | Terminal expansion: • Increase with 103,000 m2 • Eight new gates for wide-body aircraft • Capacity increase from 20 mppa to 24 mppa | 1200 | Completed | Completed in October 2023
01 Europe | Finland | Helsinki (2) | HEL | Expansion |  |  | X |  |  | X |  | New DHL cargo facility: • 16,000 m2 • 90 loading bays | 100 | Under construction | Scheduled to be completed in the second half of 2025 | 2023-08-30
01 Europe | France | Bordeaux | BOD | Expansion |  | X | [5 empty] | Passenger terminal expansion: • 600 m2 expansion of LCC terminal • Connection building linking halls A and B | 250 (connection building only) | Pre-construction | LCC terminal expansion scheduled to start in October 2024 and completed in April 2025 Connection building to start construction in 2026 | 2024-02-16
01 Europe | France | Lille | LIL | Expansion |  | X | [5 empty] | Renovation and expansion of the passenger terminal: • Capacity to increase from 2 to 4 mppa | 110 | Pre-construction | • Project was approved by the state in July 2022 • No information on construction timeline | 2023-05-13
01 Europe | France | Marseille (1) | MRS | Expansion |  | X | [5 empty] | Terminal expansion: • New passenger terminal of 22,000 m2 • Reconfiguration of 28,000 m² of terminal space | 260 | Under construction | Completion scheduled for summer of 2024
01 Europe | France | Marseille (2) | MRS | Expansion |  | X | [5 empty] | Long-term development: • New pier with 12 boarding bridges • Increase of capacity to 12 mppa | TBD | Long-term development | Long-term development
01 Europe | France | Nantes-Atlantique | NTE | Expansion & Renovation |  | X |  |  |  | X |  | Terminal renovation and runway extension: • In an effort to reduce noise in nearby communities, runway will be extended 400 m southwards to 3300 m but overall operational length will decrease. The project will offset the northern touchdown point 650 m southwards, leading effectively to a net reduction in length of 250 m | 500 | Planning | Tender cancelled in October 2023 | 2024-01-27
01 Europe | France | Nice-Côte d'Azur | NCE | Expansion |  | X | [5 empty] | Terminal expansion: • 25,000 m2 expansion Terminal 2 including check-in and baggage reclaim hall • New pier with six boarding lounges, | 200 | Under construction | Construction to start in 2023 Scheduled to be completed in 2025
01 Europe | France | Paris-de Gaulle (1) | CDG | Expansion | [6 empty] | X | New direct rail link between Paris-Gare de l'Est and Paris-CDG: • Expansion of TG station at T2 with dedicated platforms • New tunnel underneath southern parallel runway and platform | 2600 | Under construction | Scheduled to be completed in 2027 | 2023-05-16
01 Europe | France | Paris-de Gaulle (2) | CDG | Expansion |  | X | [5 empty] | New Terminal 4: • Located west of T1 and north of T2 • Rectangular terminal with linear boarding concourse • 34 stands for mostly wide body aircraft • Capacity of 40 mppa, raising total capacity to over 120 mppa | 8,000-10000 | Cancelled | • T4 Announced in early 2018 • T4 cancelled in February 2021, with Covid slowdown and climate change cited as reasons | 2024-01-27
01 Europe | France | Paris-de Gaulle (3) | CDG | Expansion |  | X | [5 empty] | Terminal expansion (speculative): • Expansion Terminal 3 for LCCs (EasyJet), allowing AF to occupy all of T2 complex • Further expansion T2 | TBD | Planning | As of May 2023, ADP is updating a Master Plan for the airport, in which the question of how to increase capacity will be addressed | 2024-02-11
01 Europe | France | Paris-Orly | ORY | Expansion | [6 empty] | X | Multimodal station: • Connecting road, bus, and metro • Underground bus station • 10-storey car park | n/a | Under construction | Construction to be finalized in 2027 | 2023-05-16
01 Europe | Germany | Berlin | BER | Expansion |  | X |  |  |  | X |  | Terminal expansion: • New passenger boarding satellite | TBD | Long-term development |  | 2024-01-27
01 Europe | Germany | Berlin | BER | Expansion | [6 empty] | X | Airport city development HORIZN BER CITY • 555,000 m² total area in between two runways, east of main terminal | TBD | Planning | • Tender was launched in October 2023 • 20 year development horizon | 2024-01-27
01 Europe | Germany | Cologne/Bonn | CGN | Expansion |  | X |  |  |  |  | X | Various projects: • Terminal 2 expansion • Construction new parking garage, • Second general air cargo hall • New airport administration building | Feasibility | TBD | Long term project | 2024-02-16
01 Europe | Germany | Frankfurt (1) | FRA | Expansion |  | X | [5 empty] | New terminal 3: • 19 mppa capacity in first phase, raising total capacity from 65 to 84 mppa • T3 capacity of 25 mppa in ultimate development | 4800 | Under construction | Opening postponed to spring 2026
01 Europe | Germany | Frankfurt (2) | FRA | Renovation |  | X | [5 empty] | Renovation Terminal 2: • Integration with T1 to become Star Alliance terminal • Includes centralized security area enabling seamless transfers between T1 and T2 | TBD | Planning | Project will be executed between 2026 and 2029 | 2024-01-28
01 Europe | Germany | Frankfurt (3) | FRA | Expansion |  |  | X |  |  |  |  | Modernization of cargo facilities: • Construction of new high-bay warehouse • Automated transport system • Upgrades or replacements of existing buildings and warehouses | 540 | Under construction | To be completed by 2030 | 2024-01-28
01 Europe | Germany | Leipzig-Halle | LEJ | Expansion | [5 empty] | X |  | Airfield expansion: • Construction of 36 new aircraft stands for DHL • Rehabilitation of the northern runway and expansion of the southern runway | 563 | Planning